## Sheet1
phase | sequence_no | trade | work_item | status | why_critical | linked_submission_category | recommended_doc_code
P01 Earthwork | EW-005 | MEP/Civil | Underground services as-built capture before backfill | Added | Prevents hidden service conflicts and rework | DOC | DOC-EW-001
P02 Shell&Core | SC-004 | Architectural | Masonry trade sequence controls | Added | Often omitted in structure-centric plans | MS | MS-SC-002
P02 Shell&Core | SC-005 | MEP/Civil | Builder's work and embedded items coordination | Added | Avoids post-pour core cutting and NCR | ITP | ITP-SC-002
P02 Shell&Core | SC-006 | Facade | Facade embeds and anchors early controls | Added | High impact on facade geometry/tolerance | MS | MS-SC-003
P03 Fitout | FO-001 | Architectural | Mockup room and sample board approval gate | Added | Brand/luxury quality baseline | DOC | DOC-FO-001
P03 Fitout | FO-002 | Architectural | Gypsum partition/ceiling sequence | Added | Frequent coordination and closure failure | MS | MS-FO-001
P03 Fitout | FO-003 | Architectural | Stone/tile dry-lay approvals | Added | Luxury finish alignment and tone control | DOC | DOC-FO-002
P03 Fitout | FO-006 | MEP | Kitchen utility/drainage and grease tests | Added | Hotel BOH operational risk | TEST | TST-FO-003
P03 Fitout | FO-007 | Firestopping | Shaft/riser firestopping closure checks | Added | Life safety and authority approvals | ITP | ITP-FO-001
P03 Fitout | FO-008 | Architectural | Special finishes sequence controls | Added | High defect risk in luxury public areas | MS | MS-FO-002
P05 Test&Commissioning | TC-004 | Life Safety | Fire alarm cause-and-effect integrated test | Added | Critical for life safety approvals | TEST | TST-TC-002
P05 Test&Commissioning | TC-005 | Electrical | Emergency power and load shedding scenarios | Added | Operational resilience requirement | TEST | TST-TC-003
P05 Test&Commissioning | TC-006 | ELV/BMS | ELV integration test sequence | Added | Interface issues usually discovered late | TEST | TST-TC-004
P06 Handover | HD-005 | FM/Asset | Asset register + CMMS import delivery | Added | Operations transition dependency | DOC | HDO-005