## Sheet1
project | phase | package | required_document | submission_category | mandatory | contractual_due_days_before_work | long_lead_flag | procurement_trigger_date | linked_shop_drawing | linked_method_statement | linked_itp | linked_mir | risk_if_delayed | stage | responsible_org | reviewer | review_status | gate | remarks
Luxury Hotel QAQC | P01 Earthwork | Method Statement Package | Excavation and Shoring Method Statement | MS | Yes | 14 | No |  | Yes | Yes | Yes | No | H | Pre-Execution | Main Contractor | QAQC Manager |  | G1
Luxury Hotel QAQC | P01 Earthwork | Method Statement Package | Backfilling and Compaction Method Statement | MS | Yes | 10 | No |  | Yes | Yes | Yes | No | M | Pre-Execution | Main Contractor | QAQC Manager |  | G1
Luxury Hotel QAQC | P01 Earthwork | Material Approval Package | Backfill Material Approval with Test Certificates | MIR | Yes | 14 | No |  | No | No | No | Yes | H | Pre-Procurement | Main Contractor | QAQC Manager |  | G1
Luxury Hotel QAQC | P01 Earthwork | Inspection Package | Earthworks ITP with Hold/Witness Points | ITP | Yes | 10 | No |  | Yes | Yes | Yes | Yes | H | Pre-Execution | Main Contractor | QAQC + Consultant |  | G2
Luxury Hotel QAQC | P01 Earthwork | Closeout Package | Underground Services As-Built Before Backfill | DOC | Yes | 2 | No |  | Yes | No | No | No | H | Post-Execution | MEP Contractor | QAQC + Consultant |  | G3 | Commonly missed
Luxury Hotel QAQC | P02 Shell&Core | Method Statement Package | Concrete Formwork/Rebar/Pour Method Statement | MS | Yes | 14 | No |  | Yes | Yes | Yes | No | H | Pre-Execution | Main Contractor | QAQC Manager |  | G1
Luxury Hotel QAQC | P02 Shell&Core | Material Approval Package | Rebar/Coupler/Cementitious Material Approvals | MIR | Yes | 21 | Yes |  | No | No | No | Yes | H | Pre-Procurement | Main Contractor | QAQC Manager |  | G1
Luxury Hotel QAQC | P02 Shell&Core | Inspection Package | Concrete Structural ITP incl. Pre-pour Checklist | ITP | Yes | 10 | No |  | Yes | Yes | Yes | Yes | H | Pre-Execution | Main Contractor | QAQC + Consultant |  | G2
Luxury Hotel QAQC | P02 Shell&Core | Inspection Package | Builder's Work and Embedded Item Coordination ITP | ITP | Yes | 10 | No |  | Yes | Yes | Yes | No | H | Pre-Execution | Main + MEP Contractor | QAQC + Consultant |  | G2 | Prevents rework
Luxury Hotel QAQC | P02 Shell&Core | Method Statement Package | Masonry Installation Method Statement | MS | Yes | 10 | No |  | Yes | Yes | Yes | No | M | Pre-Execution | Main Contractor | QAQC Manager |  | G1 | Added missing trade
Luxury Hotel QAQC | P02 Shell&Core | Method Statement Package | Facade Embed/Anchor Method Statement | MS | Yes | 21 | Yes |  | Yes | Yes | Yes | No | H | Pre-Execution | Facade Contractor | QAQC + Consultant |  | G3 | Hotel tower critical
Luxury Hotel QAQC | P03 Fitout | Pre-Execution Package | Guestroom Mockup and Sample Board Approval | DOC | Yes | 21 | No |  | Yes | No | No | No | H | Pre-Execution | Main Contractor | Consultant + Client |  | G3 | Brand critical
Luxury Hotel QAQC | P03 Fitout | Method Statement Package | Drywall and Gypsum Ceiling Method Statement | MS | Yes | 10 | No |  | Yes | Yes | Yes | No | H | Pre-Execution | Main Contractor | QAQC Manager |  | G1 | Added missing trade
Luxury Hotel QAQC | P03 Fitout | Method Statement Package | Special Finishes Method Statement (Stone/Wood/Metal) | MS | Yes | 14 | Yes |  | Yes | Yes | Yes | No | H | Pre-Execution | Main Contractor | QAQC Manager |  | G1 | Luxury finish risk
Luxury Hotel QAQC | P03 Fitout | Inspection Package | Wet Area Waterproofing ITP and Flood Test Plan | ITP | Yes | 10 | No |  | Yes | Yes | Yes | Yes | H | Pre-Execution | Main Contractor | QAQC + Consultant |  | G2
Luxury Hotel QAQC | P03 Fitout | Inspection Package | Concealed MEP Pre-Close Test and Inspection Pack | TEST | Yes | 5 | No |  | Yes | Yes | Yes | Yes | H | Pre-Closure | MEP Contractor | QAQC + Consultant |  | G4
Luxury Hotel QAQC | P03 Fitout | Inspection Package | Shaft/Riser Firestopping Closure Inspections | ITP | Yes | 5 | No |  | Yes | Yes | Yes | No | H | Pre-Closure | Main Contractor | QAQC + Consultant |  | G2 | Often missed
Luxury Hotel QAQC | P03 Fitout | Testing Package | Kitchen Utility/Drainage/Grease Testing | TEST | Yes | 5 | No |  | No | Yes | Yes | Yes | H | Pre-Closure | MEP Contractor | QAQC + Consultant |  | G4 | Hotel BOH critical
Luxury Hotel QAQC | P04 Snag | Closeout Package | Snag Register with Severity and SLA | DOC | Yes | 3 | No |  | No | No | No | No | M | Post-Execution | Main Contractor | QAQC Manager |  | G3
Luxury Hotel QAQC | P04 Snag | Closeout Package | NCR/CAPA Closure Evidence and Reinspection | TEST | Conditional | 2 | No |  | No | No | No | No | H | Post-Execution | Main Contractor | QAQC + Consultant |  | G4
Luxury Hotel QAQC | P05 Test&Commissioning | Method Statement Package | System-wise Commissioning Method Statement | MS | Yes | 14 | No |  | Yes | Yes | Yes | No | H | Pre-Execution | Commissioning Team | QAQC Manager |  | G1
Luxury Hotel QAQC | P05 Test&Commissioning | Testing Package | Calibration Certificates for Test Instruments | MIR | Yes | 3 | No |  | No | No | No | Yes | H | Pre-Test | Commissioning Team | QAQC Manager |  | G1 | ISO 9001 linked
Luxury Hotel QAQC | P05 Test&Commissioning | Testing Package | TAB + Functional Performance Test Records | TEST | Yes | 2 | No |  | No | Yes | Yes | No | H | Execution | Commissioning Team | QAQC + Consultant |  | G4
Luxury Hotel QAQC | P05 Test&Commissioning | Testing Package | Fire Alarm Cause&Effect Integrated Test | TEST | Yes | 5 | No |  | No | Yes | Yes | No | H | Execution | Commissioning Team | QAQC + AHJ |  | G4 | Life safety
Luxury Hotel QAQC | P05 Test&Commissioning | Testing Package | Emergency Power/ATS/Load Shedding Test | TEST | Yes | 5 | No |  | No | Yes | Yes | No | H | Execution | Commissioning Team | QAQC + Consultant |  | G4
Luxury Hotel QAQC | P05 Test&Commissioning | Testing Package | ELV Interface and Integration Test Records | TEST | Yes | 5 | No |  | No | Yes | Yes | No | M | Execution | ELV Contractor | QAQC + Operator |  | G4
Luxury Hotel QAQC | P06 Handover | Handover Package | Approved As-Built Drawing Register | DOC | Yes | 14 | No |  | Yes | No | No | No | H | Pre-Handover | Main Contractor | QAQC + Consultant |  | G5
Luxury Hotel QAQC | P06 Handover | Handover Package | O&M Manuals and Systems Manual | DOC | Yes | 14 | No |  | Yes | No | No | No | H | Pre-Handover | Main Contractor | QAQC + Client |  | G5
Luxury Hotel QAQC | P06 Handover | Handover Package | Training Plan + Attendance + Competency Records | DOC | Yes | 7 | No |  | No | No | No | No | M | Pre-Handover | Main Contractor | QAQC + Operator |  | G5
Luxury Hotel QAQC | P06 Handover | Handover Package | Warranty Matrix + Spare Parts Register | DOC | Yes | 7 | No |  | No | No | No | No | M | Pre-Handover | Main Contractor | QAQC + Client |  | G5
Luxury Hotel QAQC | P06 Handover | Handover Package | Asset Register + CMMS Upload Template | DOC | Yes | 7 | No |  | No | No | No | No | H | Pre-Handover | Main Contractor | QAQC + FM |  | G5 | Commonly missed