## Sheet1
project | phase | section | check_item | required | reference | gate | criticality | evidence_required | notes
Luxury Hotel QAQC | P01 Earthwork | Method Statement | Scope area and WBS clearly defined | Yes | Project QA Plan | G1 | H | Approved MS
Luxury Hotel QAQC | P01 Earthwork | Method Statement | Spec and code clause references included | Yes | Contract Spec | G1 | H | Referenced clauses
Luxury Hotel QAQC | P01 Earthwork | ITP | Linked ITP and hold witness points defined | Yes | ITP Procedure | G2 | H | Approved ITP
Luxury Hotel QAQC | P01 Earthwork | Pre-Inspection | Control points and benchmarks verified | Yes | Survey Spec | G3 | H | Signed survey record | Commonly missed
Luxury Hotel QAQC | P01 Earthwork | Pre-Inspection | Prerequisite approvals identified (SD/MIR/permits) | Yes | Submission Matrix | G3 | H | Approval log
Luxury Hotel QAQC | P01 Earthwork | MIR | Technical datasheet and certificates submitted | Yes | Material Spec | G1 | H | TDS + COC/COA
Luxury Hotel QAQC | P01 Earthwork | Testing | Test standard and acceptance criteria numeric | Yes | ASTM/BS EN | G4 | H | Test plan + criteria
Luxury Hotel QAQC | P01 Earthwork | Testing | Sampling frequency and lot plan approved | Yes | ITP | G4 | M | Lot sampling plan
Luxury Hotel QAQC | P01 Earthwork | Closeout | Underground services captured before backfill | Yes | As-built Procedure | G3 | H | Marked-up as-built | Hotel utility risk
Luxury Hotel QAQC | P02 Shell&Core | Method Statement | Pre-pour method statement approved | Yes | Concrete Spec | G1 | H | Approved MS
Luxury Hotel QAQC | P02 Shell&Core | ITP | Pre-pour hold point checklist signed | Yes | Concrete ITP | G2 | H | Signed checklist
Luxury Hotel QAQC | P02 Shell&Core | Interface | Builder's work and MEP sleeves coordinated | Yes | Coordination Drawings | G2 | H | Interface checklist | Major rework preventer
Luxury Hotel QAQC | P02 Shell&Core | MIR | Rebar/coupler approvals and traceability verified | Yes | Rebar Spec | G1 | H | Mill cert + approval
Luxury Hotel QAQC | P02 Shell&Core | Testing | Concrete tests and tolerance surveys complete | Yes | ASTM + Project Spec | G4 | H | Test reports + survey
Luxury Hotel QAQC | P02 Shell&Core | Trade Control | Masonry method and inspection controls approved | Yes | Masonry Spec | G1 | M | Approved MS/ITP | Often missed trade
Luxury Hotel QAQC | P02 Shell&Core | Facade Interface | Facade embed/anchor controls approved early | Yes | Facade Spec | G3 | H | Embed approval records | Luxury facade risk
Luxury Hotel QAQC | P03 Fitout | Mockup | Mockup room and sample boards approved | Yes | Brand/Project Standards | G3 | H | Signed mockup approvals | Hotel critical
Luxury Hotel QAQC | P03 Fitout | Method Statement | Gypsum ceiling/partition sequence approved | Yes | Finishes Spec | G1 | H | Approved MS | Missing in prior version
Luxury Hotel QAQC | P03 Fitout | Method Statement | Special finishes installation controls approved | Yes | Finishes Spec | G1 | H | Approved MS + mockups | Luxury quality driver
Luxury Hotel QAQC | P03 Fitout | Pre-Closure | Concealed MEP pre-close tests complete | Yes | MEP Specs | G4 | H | Signed test records | Must before closure
Luxury Hotel QAQC | P03 Fitout | Pre-Closure | Shaft/riser firestopping verified before closure | Yes | Firestop Spec | G2 | H | Inspection records | Often forgotten
Luxury Hotel QAQC | P03 Fitout | Wet Areas | Waterproofing flood test passed | Yes | Wet Area Spec | G4 | H | Flood test report
Luxury Hotel QAQC | P03 Fitout | BOH | Kitchen utility and drainage tests accepted | Yes | Public Health Spec | G4 | H | Test reports | Hotel BOH critical
Luxury Hotel QAQC | P04 Snag | Closeout | Snag severity matrix and SLA applied | Yes | Snag Procedure | G3 | M | Snag register
Luxury Hotel QAQC | P04 Snag | Closeout | Reinspection completed and evidence attached | Yes | QA Plan | G4 | H | Closure inspection records
Luxury Hotel QAQC | P04 Snag | NCR/CAPA | NCR CAPA and retest evidence complete where applicable | Yes | NCR Procedure | G5 | H | NCR closure pack
Luxury Hotel QAQC | P05 Test&Commissioning | Method Statement | System-wise commissioning MS approved | Yes | Cx Spec | G1 | H | Approved MS
Luxury Hotel QAQC | P05 Test&Commissioning | Testing | Instrument calibration certificates in date | Yes | ISO 9001 7.1.5 | G1 | H | Calibration certs
Luxury Hotel QAQC | P05 Test&Commissioning | Testing | TAB and FPT acceptance achieved | Yes | ASHRAE/NEBB | G4 | H | TAB/FPT reports
Luxury Hotel QAQC | P05 Test&Commissioning | Integrated Testing | Fire alarm cause-effect and life safety integration passed | Yes | NFPA/Local Fire Code | G4 | H | IST records | Hotel life safety critical
Luxury Hotel QAQC | P05 Test&Commissioning | Integrated Testing | Emergency power failover and load shedding tested | Yes | Electrical Spec | G4 | H | Test reports
Luxury Hotel QAQC | P05 Test&Commissioning | Integrated Testing | ELV and BMS interfaces tested and signed | Yes | ELV Spec | G4 | M | Interface test sheets | Often late issue
Luxury Hotel QAQC | P06 Handover | Handover | As-built register complete and approved | Yes | Handover Procedure | G5 | H | Approved as-built register
Luxury Hotel QAQC | P06 Handover | Handover | O&M and systems manual complete and indexed | Yes | O&M Spec | G5 | H | Manual transmittal
Luxury Hotel QAQC | P06 Handover | Handover | Training attendance and competency records complete | Yes | Training Plan | G5 | M | Signed training records
Luxury Hotel QAQC | P06 Handover | Handover | Warranty and spare parts register accepted | Yes | Contract Requirements | G5 | M | Warranty matrix + spare list
Luxury Hotel QAQC | P06 Handover | Handover | Asset register and CMMS import delivered | Yes | FM Requirements | G5 | H | CMMS file + asset tags | Commonly forgotten
Luxury Hotel QAQC | All Phases | Decision | Disposition assigned A/B/C/D/E with comments | Yes | Review Workflow | All | H | Disposition log | A=Approved B=Approved with comments C=Revise&Resubmit D=Rejected E=On Hold